## Workplan
Phase & Timeline | Execution Type | Primary Goals | Responsible Team Member | Dependencies & Bottlenecks
Phase 1: Infrastructure & Data | Sequential | Deploy Docker cluster, set up Kafka topics (raw_prompts, clean_prompts and the intermediate topics the stages need), and write a basic Python producer. | Blendi & Nándor | Nobody can test their River streaming pipelines until Blendi has Kafka running and Nándor has the database ready to accept outputs.
|  | Spin up PostgreSQL container and define the table schemas for metrics and reviews. | Nándor
(Oct 13 - Oct 25)
|  | Gather, clean, and format the adversarial and benign datasets. Push initial data to PostgreSQL. | Emma & Shahed
|  | Research concept-drift detection techniques and River; define initial drift metrics and test using simulated prompt data. | Francesca
Phase 2: Core Development | Parallel | Train classical binary classifier (benign vs malicious), using TF-IDF and Logistic Regression (Batch 1) | Shahed | Emma, Francesca, Shahed and Nándor can code their Python logic entirely independently using mock JSON data streams before connecting to the live Kafka topics.
|  | Train embedding/transformer-based binary classifier and compare against Batch 1 on seen and unseen attacks (Batch 2). Decide on the best one and export it for P4. | Emma
(Oct 26 - Nov 12) |  | Train attack-type classifier (Batch 3). It is deployed inside P4, next to the binary model. | Emma & Shahed
|  | Build the LangChain Agent with 2–3 named tools. | Nándor & Blendi
|  | Develop Prompt Ingestion and Enrichment (P1 & 2). | Blendi
|  | Develop Threat Detection and Classification (P3 & 4). P4 loads the winning Batch 1/2 model and runs the Batch 3 attack-type classifier alongside it. | Emma
|  | Develop Anomaly and Drift Monitoring (P5 & 6). P6 drift alerts also trigger the retraining container. | Francesca
|  | Develop Decision Routing and Attack Pattern Analysis (P7 & 8). P7 also receives the throttling decision from P10, so a flooding IP is blocked straight away. | Shahed
|  | Develop Burst Detection and Rate Limiting (P9 & 10). P10 sends throttling decisions directly to P7 and to PostgreSQL (for learning). | Nándor
|  | Develop retraining workflow using reviewed, labelled prompts (Batch 4), triggered on a schedule and by P6 drift alerts. | Francesca
Phase 3: Integration & Dashboards | Collaborative | Integrate the 10 streaming processing pipelines, connecting Kafka, PostgreSQL and the LangChain Agent. | All | P7 (Routing) must be working to correctly feed the review_queue to the Streamlit UI and the clean_prompts to the LangChain agent.
|  | Run and document the experiments: | All
(Nov 12 - Nov 22) |  | Guard latency and throughput | Emma
|  | Drift detection delay on simulated new attack styles | Francesca
|  | Burst detection and throttling on simulated attacker IPs | Nándor
|  | Retraining before vs. after | Shahed
|  | Demo: an attack succeeds without the guard and is blocked with it | Blendi
|  | Connect PostgreSQL to the Streamlit UI. | Nándor
|  | Develop Streamlit Dashboards, each with at least two meaningful graphs: | All
|  | Blocked vs. allowed over time | Blendi
|  | Model comparison on seen vs. unseen attacks | Emma
|  | Drift alerts | Francesca
|  | Attack-type breakdown and Top-10 | Shahed
|  | Review queue status with burst/throttling activity | Nándor
Phase 4: Final Wrap-Up | Parallel | Write the document abstract, introduction, and format the 10-15 academic references. | Francesca & Shahed
|  | Document the system architecture and testing/experiments sections. | Blendi & Emma
(Nov 22 - Nov 26)
|  | Clean up the GitHub repository, ensure code runs via a single docker-compose up. | Nándor
Phase 5: Defence | Collaborative | Prepare the slides | All
(Nov 26 - Dec 4) |  | Discuss the entire flow of the project together to ensure we understand each other's stages. | All
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These batch tasks align with the Batch Training & Retraining box in the architecture. Batch processing creates and updates the models.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are the streaming processes in the Guard. P4 specifically uses use the trained models created in the batch processing tasks to analyse prompts in real time.

## Streaming Pipelines
Functional Pipeline | Streaming process | Stage in architecture
Prompt Ingestion and Enrichment | 1. Ingest incoming prompts from Kafka and clean text | Stream Ingestion
| 2. Enrich prompts with source information and threat context | IP Join & Threat Cache
Threat Detection and Classification | 3. Compare incoming prompts with known attack patterns | Stateful Similarity Probing
| 4. Classify prompts with the winning Batch 1 or 2 model and assign an attack type with the Batch 3 classifier | Best ML Inference & Attack-Type Classifier
Anomaly and Drift Monitoring | 5. Identify unusual or previously unseen prompt behaviour | Half-Space Trees
| 6. Monitor changes in the data distribution over time and trigger a retraining alert when drift is detected | Drift Monitor
Decision Routing and Attack Pattern Analysis | 7. Decide whether to allow, block or flag prompts (also using the throttling decision from P10) | Score Routing & Splitting
| 8. Calculate the most common attack patterns (by attack type from P4) over a rolling window | Top-10 Window Aggregations
Burst Detection and Rate Limiting | 9. Detect sudden increases in suspicious activity | Burst Detection Window
| 10. Restrict excessive requests from suspicious sources; send the throttling decision to P7 and PostgreSQL | Rate Limiter Throttling

## Technical Decisions
Topic | Description / Decision
Datasets | Training/validation/testing: NeurAlchemy Prompt Injection Dataset, containing benign and malicious prompts. Exclude control and chain_of_thought categories. External evaluation: deepset/prompt-injections and jackhhao/jailbreak-classification, used only for testing generalisation.
Batch 1 & 2 models | B1: TF-IDF + Logistic Regression. B2: Frozen transformer embeddings + Logistic Regression. Both use identical training, validation and test splits for fair comparison.
Unseen-attack evaluation | Evaluate Batch 2 on the NeurAlchemy test set (seen attack families) and two entirely held-out external datasets (unseen sources). Also evaluate Batch 1 on the same datasets for comparison. Optionally hold out an entire attack family for additional testing. Report precision, recall, F1, FPR, ROC-AUC and inference latency, alongside a length-only baseline.
Best-model selection | Compare Batch 1 and Batch 2 using validation-set macro-F1 and deploy the selected binary classifier in P4. Evaluate final performance on the standard and held-out external test datasets.
Batch 3 | Use NeurAlchemy's category labels to train a multiclass attack-type classifier. Proposed grouping into six broader categories: instruction manipulation, jailbreak/persona manipulation, obfuscation, information extraction, indirect injection/agent manipulation, and adversarial attacks.
Batch model deployment | The attack-type classifier (Batch 3) should run in the streaming path inside P4, alongside the binary model (either Batch 1 or 2).
LangChain Agent Tools | We will implement one LangChain agent with two tools: calculator(a, operation, b) for basic arithmetic and lookup_course_info(topic) for retrieving information from a fixed local course-information file. Only prompts marked ALLOW by P7 will reach the agent. Agent responses, tool calls, and execution time will be recorded in PostgreSQL.
Guard demonstration | We will identify a reproducible attack that makes the unguarded agent violate its instructions, such as revealing a dummy secret included in its test configuration. We will then submit the same attack with the guard enabled and demonstrate that it is blocked before agent execution.
Prompt identify and bursts | The producer will attach a source_ip to every prompt. Manual submissions will use the request IP; dataset replay will assign simulated benign and attacker IPs. Some attacker IPs will send concentrated bursts so P9 and P10 can be tested.
Drift to retraining | P6 drift alerts trigger the retraining container, in addition to the scheduled retraining.
Rate limiter to P7 | P10 sends the throttling decision directly to P7, so a flooding IP is blocked straight away, and also writes it to PostgreSQL for learning.
Kafka topics | raw_prompts and clean_prompts. Additional intermediate topics will be defined during implementation.
Experiments | Latency/throughput, drift delay, burst and throttling, retraining before/after, guard on/off demo.
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Links to datasets: neuralchemy/Prompt-injection-dataset · Datasets at Hugging Face deepset/prompt-injections · Datasets at Hugging Face jackhhao/jailbreak-classification · Datasets at Hugging Face